## Event action tracker
EVENT ACTION TRACKER
TITLE - EVENT NAME AND LOCATION |  |  | Event date:
This action tracker covers event announcements, equipment lists, racing documents, HSE items and event management. It is intended to assist the RO coordinate Race Team activities and ensure relevant event resources are ready in a timely manner. NB Many of these items may not be necessary and can be ignored.
Announcements | WHO | LEAD TIME (DAYS) | LEAD TIME (WEEKS) | DATE REQUIRED | DATE COMPLETED | STATUS
Appoint RO and Event Secretary |  | 56 | 8 | [5 empty] | Not started
Book sailing venue |  | 49 | 7 | [5 empty] | In progress
Draft NOR |  | 42 | 6 | [5 empty] | Completed
Review draft NOR with MYA SD Racing Secretary & MYA SD Committee |  | 35 | 5 | [5 empty] | N/A
Publish agreed NOR |  | 28 | 4
Advertise (MYA SD website and via MYA SD Club Secretaries) |  | 28 | 4
Advertise NOR/event reminders |  | 14 | 2
Send Personal Medical Information forms to entrants and all race team members |  | 7 | 1
Advertise NOR/event reminders |  | 7 | 1
Equipment Requirements (*** available from MYA SD resources) | WHO | LEAD TIME (DAYS) | LEAD TIME (WEEKS) | DATE REQUIRED | DATE COMPLETED | STATUS
Publicity (publish NOR, 2 x reminder to club secs, etc.) |  | 28 | 4
Prepare buoys and ground tackle | ` | 14 | 2
Course Board + Marker Pens |  | 7 | 1
Notice Board |  | 7 | 1
Race Team Hi Vis Vests *** |  | 7 | 1
Throw Lines |  | 7 | 1
Protest Boats *** |  | 7 | 1
Whistle, Manual Horn *** |  | 7 | 1
Wind Indicator *** |  | 7 | 1
Start Tape Sound System + Spare + Charger |  | 7 | 1
Walkie-talkies, chargers, etc. *** |  | 7 | 1
Race Control Clipboard for Start and Finish data + waterproof cover *** |  | 7 | 1
Publicity Banner/Flags *** |  | 7 | 1
Laptop / printer |  | 7 | 1
Event Timepiece |  | 7 | 1
Dinghy + Outboard + Oars + Lifejackets + fuel |  | 7 | 1
Spare dinghy, electric outboard, battery, lifejacket, etc. |  | 7 | 1
Team for setting of markers - check buoys / ground tackle, etc. |  | 7 | 1
Digital camera for event media coverage |  | 7 | 1
Measurement Equipment (Scales, Test Weights, Ruler, Tape) |  | 7 | 1
Observer Notepads and Pencils *** |  | 7 | 1
Gazebo, chairs and collapsible table |  | 7 | 1
Tape Recorder for Finish Positions |  | 7 | 1
HMS software for scoring |  | 7 | 1
Fleet Management Board showing competitor, sail no, frequency *** |  | 7 | 1
Print hardcopy documents (*** available from MYA SD resources) | WHO | LEAD TIME (DAYS) | LEAD TIME (WEEKS) | DATE REQUIRED | DATE COMPLETED | STATUS
Computer Scoring System for HMS *** |  | 7 | 1
Heat Management System *** |  | 7 | 1
MYA Scottish District Standard Sailing Instructions *** |  | 7 | 1
Racing Rules of Sailing 2021-24 *** |  | 7 | 1
Equipment Rules of Sailing *** |  | 7 | 1
Class Rules *** |  | 7 | 1
Notice of Race |  | 7 | 1
Protest forms *** |  | 7 | 1
Observer Marshall Control Sheet *** |  | 7 | 1
Observer Incident Form *** |  | 7 | 1
No certs form *** |  | 7 | 1
HSE | WHO | LEAD TIME (DAYS) | LEAD TIME (WEEKS) | DATE REQUIRED | DATE COMPLETED | STATUS
HSE Plan, Event Risk Assessment, Location Details, Responsible Person etc. |  | 7 | 1
Grab Bag, First Aid Kit, Throw Line |  | 7 | 1
Defibrilator location |  | 7 | 1
Print and laminate location-specific HSE documents |  | 7 | 1
Brief / train / test radio operators on use of walkie-talkies |  | 2 | 0.28571
Event management - document hard copies | WHO | LEAD TIME (DAYS) | LEAD TIME (WEEKS) | DATE REQUIRED | DATE COMPLETED | STATUS
Sail number allocations |  | 7 | 1
Trophies (only required for some MYA SD Championships) |  | 7 | 1
Race/heat finish position sheets |  | 7 | 1
Master Entry List |  | 2 | 0.28571
Seeding Heats (if applicable) |  | 2 | 0.28571
Event Master Manual Result Sheet |  | 2 | 0.28571
Race Team | WHO | LEAD TIME (DAYS) | LEAD TIME (WEEKS) | DATE REQUIRED | DATE COMPLETED | STATUS | Radio | Hi-Viz vests
RO - on the day can assist course setting / start (NB Issue radio #1) |  | 56 | 8 |  |  |  | 1 | 1
Event Secretary |  | 56 | 8
Registration / certs / Personal Medical Information form (often done by Event Secretary) |  | 14 | 2 |  |  |  |  | 1
Measurer |  | 14 | 2 |  |  |  |  | 1
Scorer (& assistant?) |  | 28 | 4 |  |  |  |  | 1
Fleet Board Controller & Observer Marshall (only needed if multi-heats) |  | 28 | 4 |  |  |  |  | 1
Boatman (NB Issue radio #2) |  | 14 | 2 |  |  |  | 1 | 1
Finish Line Team (x2) - finish line judge and scribe (NB Issue radio #3) |  | 14 | 2 |  |  |  | 1 | 2
Photographer |  | 14 | 2 |  |  |  |  | 1
Sailing venue - considerations | WHO | LEAD TIME (DAYS) | LEAD TIME (WEEKS) | DATE REQUIRED | DATE COMPLETED | STATUS
1) Interface management with other venue users? (If applicable) |  | 42 | 6
2) Safety boat(s) |  | 42 | 6
3) Use of jetty(s)? (If applicable) |  | 42 | 6
4) Need for life jackets? (If applicable) |  | 42 | 6
5) Access to storage facilities (If applicable) |  | 42 | 6
5) Car parking arrangements? |  | 42 | 6
6) Use of walkways and separation from public |  | 42 | 6
7) Access to Defibrilator? |  | 28 | 4
8) Prizegiving |  | 14 | 2
Note on G2: Enter as dd/mm/yy. NB When this date changes all the "Date Required" dates update
Note on H4: In cells below, click on cell, then down arrow and select choice to update status

## Race Team
Race Team | WHO | Radio | Hi-Viz vests
RO - on the day can assist course setting / start (NB Issue radio #1) |  | 1 | 1
Event Secretary
Fleet Board Controller & Observer Marshall (only needed if multi-heats) |  |  | 1
Scorer (& assistant?) |  |  | 1
Registration / certs / Personal Medical Information form (often done by Event Secretary) |  |  | 1
Measurer |  |  | 1
Boatman (NB Issue radio #2) |  | 1 | 1
Finish Line Team (x2) - finish line judge and scribe (NB Issue radio #3) |  | 1 | 2
Photographer |  |  | 1
|  | 3 | 9

## Registration Checklist
TITLE - EVENT NAME AND LOCATION
| Sail # | Name of skipper/race team member | MYA # | Boat cert | ICE details | PSN | Location of Personal Medical Information form?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36